## 1. Product Overview
Item | Description
Product Name | Tryvera - Virtual Try On
Product Vision/ Purpose | To enable users to virtually try on clothes using AI-based image processing and 3D overlay technology.
The goal is to create an interactive and personalized shopping experience.
Business Goals / Key Success factors | Enhance customer experience and reduce product returns.Provide a seamless, real-time virtual try-on experience.
Provide a seamless, real-time virtual try-on experience.Integrate with e-commerce platforms for easy adoption.
Achieve high user engagement through intuitive UI and realistic rendering.
Ensure fast processing and accurate fitting suggestions.
Primary Stakeholders | Product Lead: Pranav (overseeing product development and roadmap)
Development Team: Sahil (Dev Lead), Shyam (Backend)
Frontend : Pratistha , Shamin
Test Team: Rohan (Test Lead), Rakshith (QA Member)
Research & Marketing : Vivian Raj
End Users: Online shoppers and e-commerce retailers integrating the solution.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen details | Must Have | To Do | Backend Dev - Sahil, Shyam | Auth_Test_Cases_Doc | Rohan, Rakshith
|  | US2 | As a user, I want to log in using OTP so that I can securely access my profile. | Pop Ups once registered | Must Have | To Do | Frontend - Pratistha,shamin | OTP_Login_Test_Cases | Rohan, Rakshith
|  | US3 | As a user, I want to reset my password using email OTP so that I can recover my account easily. | Login screen | Should Have | To Do | Backend Dev - Sahil, Shyam | Password_Reset_Test_Cases | Rohan, Rakshith
E2 | Dashboard | US4 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. | Dashboard UI, Graph Rendering, API Integration | Should Have | In Progress | Frontend - Pratistha ,shamin | Dashboard_Test_Cases | Rohan, Rakshith
E3 | Virtual Try-On Core | US5 | As a user, I want to upload my image and virtually try clothes so that I can see how they look on me. | Image Upload, Background Removal, 3D Overlay Algorithm, Render Engine | Must Have | In Progress | Frontend - Pratistha,backend -sahil | VTO_Test_Cases | Rohan, Rakshith
|  | US6 | As a user, I want to preview multiple clothing styles and switch between them easily. | Dynamic Image Rendering, Style Switch Functionality | To-Do | In Progress | Frontend - Pratistha,backend -sahil | Style_Switch_Test_Cases | Rohan, Rakshith
E4 | Research & Marketing | US7 | As a marketing team member, I want to analyze user engagement so that I can improve campaign strategies. | Google Analytics Integration, Dashboard Reports | Should Have | In Progress | Research & Marketing - Vivian Raj | Marketing_Test_Cases | Rohan, Rakshith
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Authentication, Dashboard MVP | None | On Track
v0.2 | 2025-11-22 | Virtual Try-On demo prototype | Requires ML model integration | On Track
v0.3 | 2025-11-29 | Virtual Try-On Core ( 3D Overlay) | Requires ML & AR model integration | On Track
v0.4 | 2025-12-06 | Style Switch Feature, Improved Rendering Engine | Depends on VTO Core | Planned
v0.5 | 2025-12-13 | Enhanced Dashboard UI | UI/Backend synchronization | Yet To Plan
v1.0 | 2025-12-20 | Final Stable Release | Full QA & Testing | Yet To Plan
v1.1 | 2025-12-27 | Marketing and Performance Optimization | Post-launch monitoring tools | Yet To Plan

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead-Rohan & Rakshith
Team communication between frontend and backend improved | Missed one stand-up due to unclear task ownership | Assign task owners clearly at sprint start | Product Lead – Pranav
Marketing insights helped define user flow better | Late feedback from test team caused delay | Include QA early in sprint planning | Research & Marketing – Vivian Raj & Shamin
Initial ML-based virtual try-on model produced realistic output | ML model was complex and required high computation time during rendering | Optimize model architecture, test lightweight ML frameworks, and consider cloud-based inference (e.g., Vertex AI) | Dev Lead – Sahil & shyam